## SolutionArchitecture Task list
Solution Architecture
Define POC
Identify POC
Workshops: Integration Architecture - ICL
Workshop: TESS Integration solution Approach for ICL
Define TMS - Inbound Wkshop # 1 (Define TMS - Inbound - Happy Path Scenario / Get Acknowledgement for each request)
Define TMS - Inbound Wkshop # 2(High Level Message Format, Error Handling)
Define TMS - Inbound Wkshop # 3 (ICL – TTMS Inbound Communication Downtime Scenarios)
Define TMS - Define TESS integration - TLS Designate Users (TESS SSO Federation- User Management & Role Management)
Define TMS - (Continue to Review the Scenarios for System Down time HLD: Error Handling, Message Processing ,Review High Level ICE Design) | Completed
Define TMS - ICE High level Design Document – TTMS Redesign
Conduct Workshop to Communicate the Integration and Security Pattern to ICL.
Define Security architecture and TESS integration - TLS Designate Users (TESS SSO Federation)
Walkthrough of the High Level Architecture - TMS
Document the High Level Architecture - TMS
Conduct Workshop to Review the High Level Architecture for ICL.
Soln. Architecture - TMS
TTMS - Integration (TMS, ICL)
Define Architecture Goals
Document Conceptual Architecture
Identify the High-level Technical Stack along with EIG
Document To-Be Arch Context View
I1: Internal review of conceptual architecture and goals
Incorporate internal review comments
TMS Inbound Integration Approach
Define & Document TMS Inbound – (Define Integration technical Approach (Web services / FTPS))
Analyse Architecturaly Significant use case documents
W1: Conduct workshop with primary stakeholders
Analysis / Design: Message Processing – Integration Channels, Auditing and Monitoring.
Document: Message Processing – Integration Channels
Document: Auditing and Monitoring.
Finalize the Communication pattern with EA and ICE- Integration Pattern (SOAP or REST)
Finalize the Security Pattern
Document the integration approach and review internally
R1: Review the integration approach with primary stakeholders
Incorporate review comments & Republish
Communicate the Integration solution – ICL.
ICL SO: Sign-off TMS Integration Approach
TMS Outbound Real Time Integration Approach
Define TMS Outbound – (Real-Time Communication Integration Approach)
Analyse Architecturaly Significant use case documents
Analysis / Design: Message Processing – Integration Channels, Auditing and Monitoring.
Document: Message Processing – Integration Channels
Document: Auditing and Monitoring.
Finalize the Communication pattern with EA and ICE- Integration Pattern (SOAP or REST)
W1: Conduct workshop with primary stakeholders
Feasibility study for real time data communication (Identify the Source) for TTMS outbound interface (++ Analyze the N/C # 1
Workshop: Feasibility study for real time data communication (Identify the Source) for TTMS outbound interface (++ Focus the N/C. & ICE ) # 2. Document the Table Details
Technical Analysis: Error & Exception Handling - Integration Flows
Finalize the Security Pattern
Document the integration approach and review internally
R1: Review the integration approach with primary stakeholders
Communicate the solution – ICL.
Incorporate review comments & Republish
ICL SO: Sign-off TMS Integration Approach
VDW Integration Approach
Define VDW Integration Approach
Security Architecture - EIG
Define Security architecture with ICE / EIG
TLS to share the Classification of the Data.
Guidelines Communication Pattern (Sync / Async)
Security Architecture - TESS
Define Security architecture and TESS integration
User Management (ICL - TMS TESS)
TTMS-ICL Roll mapping to be finalized
Define one-time initial user load and TESS role definition
User transfer and termination criteria to be discussed with ICL
User provisioning process to be discussed with ICL , TESS
Finalize the Approval Workflow for User Authorization
Discuss on TLS user's Account Inactive, Password Expiry, Account Lock Out with ICL
Avoid session misuse, handle logout warning, idle session timeout
Finalize all user provisioning requirements and get sign-off
Supplementary Specifications
Analysis the Volumetric Data : For all TTMS inbound / Outbound interface
Review the Volumetric Data : For all TTMS Inbound / Outbound interface
Workshop - 1 Supplementary Spec
User and User role management, application role
Application scalability ,usability and performance targets
Workshop 2 - Supplementry Specs
Application Disaster recovery - SLAs
Application Security
Application Performance Monitoring
Intermediate SAD Peer review review with team
Intermediate SAD Peer review review with EA
Reportig
Workshop - 3 Supplementary Spec
Intermediate SAD Peer review review with team
Supplementry Spec Review with EA
Incorporate review comments and publish the document
Review Supplementary Spec (all)
Update Supplementary Specifications document with all comments
Supplementary Specs SO: EA
Supplementary Specs Final SignOff
Develop SAD
Collate Inputs & Publish SAD
Rest JSON High-level Message Schema Preparation
Document architectural solution scenarios/decisions
Logical View workshop with EA
Document logical architecture views
Document As Is Logical View
Document To Be Logical View
Document Integration View
Integration view Workshop1 with EA
Document Inbound Integration View
Document Outbound Integration View
Integration Pattern Workshop with EA
Document Integration Patterns ( Message format,error handling, Message exchange)
MQ Integration Patterns
Document System Integrations (VDW , TOMS)
Document Security Integrations (EIG, TESS)
Document TTMS Audit Integration
Integration Pattern Workshop with EA
Document DevOps or ITOps Integration (BuildFarm, Foglight)
Security View Workshop with EA
Document Security View
Process View Workshop with EA
Document Process View
Intermediate SAD Peer review review with team
Intermediate SAD Peer review review with EA
Implementation View Workshop with EA
Document Implementation and Technology views
Document Components and Service Views
Intermediate SAD Peer review review with team
Intermediate SAD Peer review review with EA
Deployment View Workshop with EA
Document Deployment Views
Document Parallell Deployment Validation and Strategy
Document risk ,assumptions, open items.
SAD Review & Sign Off
Publish SAD , Conduct Internal Review & Incorporate Review Comments
R1: Review with primary stakeholders & Incorporate Comments
SO: Sign-off Solution Architecture Document - Iteration 3
SAD
Soln. Architecture - ICL
High Level Architecture
Document ICL Integration Architecture views
Publish SAD
R1: Review with TTMS, ICE & EA stakeholders & Incorporate Comments
ICL to Incorporate Review Comments - ICL SAD
R2: Review with TTMS, ICE & EA stakeholders & Incorporate Comments
Soln. Architecture - ICL

## Sheet1 (hidden)
Task Name
VDW Integration Approach
Define VDW Integration Approach ( Analysis of Impact / Change on existing VDW jobs, tables and integration – Joint study VDW and TTMS (Set up meeting with VDW data architect to be structure ))
Conduct Workshop -- Mapping of TTMS Tables Attributes with VDW 8 Tables. Need to under
Identify POC
NFR
Task Name
Supplementary Specifications
Analysis the Volumetric Data : For all TTMS inbound / Outbound interface
Review the Volumetric Data : For all TTMS Inbound / Outbound interface
Workshop - 1 Supplementary Spec
Create Supp. Spec (NFR)
Workshop - 2 Supplementary Spec
Review Supplementary Spec (EA)
Review Supplementary Spec (all)
Update Supplementary Spec
Supplementary Specs SO: EA
Supplementary Specs

## Sheet2 (hidden)
Task Name | Duration | Status | Baseline Estimated Start | Baseline Estimated Finish
VDW Integration Approach | 3 days | Future Task | Fri 9/11/15 | Mon 9/14/15
Define VDW Integration Approach ( Analysis of Impact / Change on existing VDW jobs, tables and integration – Joint study VDW and TTMS (Set up meeting with VDW data architect to be structure )) | 1 day | Future Task | Fri 9/11/15 | Fri 9/11/15
Conduct Workshop -- Mapping of TTMS Tables Attributes with VDW 8 Tables. Need to under | 2 days | Future Task | Mon 9/14/15 | Mon 9/14/15
Task Name | Duration | Status | Baseline Estimated Start | Baseline Estimated Finish
Supplementary Specifications | 12 days | Future Task | Thu 9/17/15 | Fri 10/2/15
Analysis the Volumetric Data : For all TTMS inbound / Outbound interface | 3 days | Future Task | Thu 9/17/15 | Mon 9/21/15
Review the Volumetric Data : For all TTMS Inbound / Outbound interface | 1 day | Future Task | Tue 9/22/15 | Tue 9/22/15
Workshop - 1 Supplementary Spec | 1 day | Future Task | Wed 9/23/15 | Wed 9/23/15
Create Supp. Spec (NFR) | 1 day | Future Task | Thu 9/24/15 | Thu 9/24/15
Workshop - 2 Supplementary Spec | 1 day | Future Task | Fri 9/25/15 | Fri 9/25/15
Review Supplementary Spec (EA) | 1 day | Future Task | Mon 9/28/15 | Mon 9/28/15
Review Supplementary Spec (all) | 1 day | Future Task | Tue 9/29/15 | Tue 9/29/15
Update Supplementary Spec | 1 day | Future Task | Wed 9/30/15 | Wed 9/30/15
Supplementary Specs SO: EA | 1 day | Future Task | Thu 10/1/15 | Thu 10/1/15
Supplementary Specs | 1 day | Future Task | Fri 10/2/15 | Fri 10/2/15
Task Name | Duration | Status | Baseline Estimated Start | Baseline Estimated Finish
Define POC | 1 day? | On Schedule | Wed 9/9/15 | Wed 9/9/15
Identify POC | 1 day? | On Schedule | Wed 9/9/15 | Wed 9/9/15

## Highlevel task (hidden)
| Start date | End date | Comments
Solution architecture document | 2015-09-11 | 2015-10-30
NFR | 2015-09-17 | 2015-10-30
Data design document | 2015-09-30 | 2015-11-15
Define POC | 2015-09-10 | 2015-09-11
Design Activity
1 JBOSS Appframework Support for Jboss Hornet Queue Configuration – Need analysis Appframework documentation 1.1 Queue Configuration and Single Queue instance with Jboss HornetQueue Setup a meeting with deepak to share the outcome of the analysis |  |  | Will depend on invfrastructure setup? Please state any other prerequirsite
2. JSON POC 2.1 JSON message schema Validator 2.2 JSON File Attachment and Compression techniques |  |  | Does not depend on the infrastructure. Please state if any other depdndency
Spring JMS with latest JBOSS appframework Support Analysis |  |  | Does not depend on the infrastructure. Please state if any other depdndency
Spring Batch Analysis - Already have the Appframework documentation |  |  | Does not depend on the infrastructure. Please state if any other depdndency
JMX control to stop and start Message listener service programmatically |  |  | Does not depend on the infrastructure. Please state if any other depdndency

## Plan
Task Name | Duration | Status | Start | Finish
TTMS Elaboration | 119 days? | On Schedule | 2015-08-10 | 2016-01-28
Integration Requirement elaboration | 99 days? | On Schedule | 2015-08-10 | 2015-12-30
Parallel Validation tool Requirement | 18 days | Future Task | 2015-10-05 | 2015-10-29
Integration requirement elaboration (Analysis, Use Case) | 99 days? | On Schedule | 2015-08-10 | 2015-12-30
Inbound: Analysis | 97 days | On Schedule | 2015-08-10 | 2015-12-28
Vessel ETA | 39.5 days | On Schedule | 2015-08-10 | 2015-10-05
VESSEL ETA- Analyze the MQ Attributes. | 10 days | Complete | 2015-08-10 | 2015-08-21
VESSEL ETA- Analysis the Validation and Exceptional scenarios | 7 days | Complete | 2015-08-24 | 2015-09-01
VESSEL ETA- Analysis if any dependencies with downstream and other interfaces | 5 days | Complete | 2015-09-02 | 2015-09-09
Analysis : On Extra Attributes in OTM / BDM | 1 day | Complete | 2015-09-10 | 2015-09-10
Analysis: Impact of ICL Elaboration - Plan for impact identified from the discussion with ICL elaboration | 3 days | On Schedule | 2015-09-10 | 2015-10-05
SEDB | 68 days | On Schedule | 2015-08-10 | 2015-11-12
VDW | 32 days | On Schedule | 2015-08-10 | 2015-09-23
Voucher FTPR | 77 days | On Schedule | 2015-08-10 | 2015-11-25
Transit | 7.5 days | Future Task | 2015-10-05 | 2015-10-14
Accruals | 41.5 days | Future Task | 2015-10-13 | 2015-12-11
Shipping schedule | 49.5 days | Future Task | 2015-10-15 | 2015-12-28
Inbound: Requirement elaboration & Use cases | 89 days? | On Schedule | 2015-08-24 | 2015-12-30
Vessel ETA | 89 days | On Schedule | 2015-08-24 | 2015-12-30
SEDB | 55 days? | On Schedule | 2015-08-28 | 2015-11-13
VDW | 21 days? | On Schedule | 2015-08-31 | 2015-09-29
Voucher FTPR | 66 days? | On Schedule | 2015-09-01 | 2015-12-04
Accruals | 65 days? | Future Task | 2015-09-14 | 2015-12-15
Transit | 23 days? | Future Task | 2015-09-17 | 2015-10-19
Shipping schedule | 68 days | Future Task | 2015-09-23 | 2015-12-30
Integration Use Cases: Inbound | 0 days | Future Task | 2015-12-28 | 2015-12-28
TTMS Outbound | 44 days | Late | 2015-08-10 | 2015-10-09
Solution Architecture | 56.5 days? | On Schedule | 2015-09-09 | 2015-11-30
Define POC | 1 day? | Complete | 2015-09-09 | 2015-09-09
Identify POC | 1 day? | Complete | 2015-09-09 | 2015-09-09
Workshops: Integration Architecture - ICL | 12 days | Future Task | 2015-09-29 | 2015-10-14
Workshop: TESS Integration solution Approach for ICL | 1 day | Future Task | 2015-09-29 | 2015-09-29
Define TMS - Inbound Wkshop # 1 (Define TMS - Inbound - Happy Path Scenario / Get Acknowledgement for each request) | 1 day | Future Task | 2015-09-30 | 2015-09-30
Define TMS - Inbound Wkshop # 2(High Level Message Format, Error Handling) | 1 day | Future Task | 2015-10-01 | 2015-10-01
Define TMS - Inbound Wkshop # 3 (ICL – TTMS Inbound Communication Downtime Scenarios) | 1 day | Future Task | 2015-10-02 | 2015-10-02
Define TMS - Define TESS integration - TLS Designate Users (TESS SSO Federation- User Management & Role Management) | 1 day | Future Task | 2015-10-05 | 2015-10-05
Define TMS - (Continue to Review the Scenarios for System Down time HLD: Error Handling, Message Sequencing.Review High Level ICE Design) | 1 day | Future Task | 2015-10-06 | 2015-10-06
Define TMS - ICE High level Design Document – TTMS Redesign | 1 day | Future Task | 2015-10-07 | 2015-10-07
Conduct Workshop to Communicate the Integration and Security Pattern to ICL. | 1 day | Future Task | 2015-10-08 | 2015-10-08
Define Security architecture and TESS integration - TLS Designate Users (TESS SSO Federation) | 1 day | Future Task | 2015-10-09 | 2015-10-09
Walkthrough of the High Level Architecture - TMS | 1 day | Future Task | 2015-10-12 | 2015-10-12
Document the High Level Architecture - TMS | 1 day | Future Task | 2015-10-13 | 2015-10-13
Conduct Workshop to Review the High Level Architecture for ICL. | 1 day | Future Task | 2015-10-14 | 2015-10-14
Soln. Architecture - TMS | 48.25 days | On Schedule | 2015-09-11 | 2015-11-18
TTMS - Integration (TMS, ICL) | 48.25 days | On Schedule | 2015-09-11 | 2015-11-18
Define Architecture Goals | 5 days | Future Task | 2015-10-06 | 2015-10-13
Document Conceptual Architecture | 1 day | Future Task | 2015-10-06 | 2015-10-07
Identify the High-level Technical Stack along with EIG | 1 day | Future Task | 2015-10-07 | 2015-10-08
Document To-Be Arch Context View | 1 day | Future Task | 2015-10-08 | 2015-10-09
I1: Internal review of conceptual architecture and goals | 1 day | Future Task | 2015-10-09 | 2015-10-12
Incorporate internal review comments | 1 day | Future Task | 2015-10-12 | 2015-10-13
TMS Inbound Integration Approach | 21 days | Future Task | 2015-10-13 | 2015-11-11
Define & Document TMS Inbound – (Define Integration technical Approach (Web services / FTPS)) | 1 day | Future Task | 2015-10-13 | 2015-10-14
Analyse Architecturaly Significant use case documents | 1 day | Future Task | 2015-10-14 | 2015-10-15
W1: Conduct workshop with primary stakeholders | 1 day | Future Task | 2015-10-15 | 2015-10-16
Analysis / Design: Message Sequencing – Integration Channels, Auditing and Monitoring. | 1 day | Future Task | 2015-10-16 | 2015-10-19
Document: Message Sequencing – Integration Channels | 3 days | Future Task | 2015-10-19 | 2015-10-22
Document: Auditing and Monitoring. | 3 days | Future Task | 2015-10-22 | 2015-10-27
Finalize the Communication pattern with EA and ICE- Integration Pattern (SOAP or REST) | 1 day | Future Task | 2015-10-27 | 2015-10-28
Finalize the Security Pattern | 1 day | Future Task | 2015-10-28 | 2015-10-29
Document the integration approach and review internally | 2 days | Future Task | 2015-10-29 | 2015-11-02
R1: Review the integration approach with primary stakeholders | 1 day | Future Task | 2015-11-02 | 2015-11-03
Incorporate review comments & Republish | 1 day | Future Task | 2015-11-03 | 2015-11-04
Communicate the Integration solution – ICL. | 4 days | Future Task | 2015-11-04 | 2015-11-10
ICL SO: Sign-off TMS Integration Approach | 1 day | Future Task | 2015-11-10 | 2015-11-11
TMS Outbound Real Time Integration Approach | 27 days | Future Task | 2015-10-08 | 2015-11-16
Define TMS Outbound – (Real-Time Communication Integration Approach) | 3 days | Future Task | 2015-10-08 | 2015-10-13
Analyse Architecturaly Significant use case documents | 2 days | Future Task | 2015-10-13 | 2015-10-15
Analysis / Design: Message Sequencing – Integration Channels, Auditing and Monitoring. | 2 days | Future Task | 2015-10-15 | 2015-10-19
Document: Message Sequencing – Integration Channels | 2 days | Future Task | 2015-10-19 | 2015-10-21
Document: Auditing and Monitoring. | 2 days | Future Task | 2015-10-21 | 2015-10-23
Finalize the Communication pattern with EA and ICE- Integration Pattern (SOAP or REST) | 1 day | Future Task | 2015-10-23 | 2015-10-26
W1: Conduct workshop with primary stakeholders | 1 day | Future Task | 2015-10-26 | 2015-10-27
Feasibility study for real time data communication (Identify the Source) for TTMS outbound interface (++ Analyze the N/C # 1 | 1 day | Future Task | 2015-10-27 | 2015-10-28
Workshop: Feasibility study for real time data communication (Identify the Source) for TTMS outbound interface (++ Focus the N/C. & ICE ) # 2. Document the Table Details | 2 days | Future Task | 2015-10-28 | 2015-10-30
Technical Analyze: Error & Exception Handling - Integration Flows | 1 day | Future Task | 2015-10-30 | 2015-11-02
Finalize the Security Pattern | 1 day | Future Task | 2015-11-02 | 2015-11-03
Document the integration approach and review internally | 3 days | Future Task | 2015-11-03 | 2015-11-06
R1: Review the integration approach with primary stakeholders | 2 days | Future Task | 2015-11-06 | 2015-11-10
Communicate the solution – ICL. | 1 day | Future Task | 2015-11-10 | 2015-11-11
Incorporate review comments & Republish | 2 days | Future Task | 2015-11-11 | 2015-11-13
ICL SO: Sign-off TMS Integration Approach | 1 day | Future Task | 2015-11-13 | 2015-11-16
VDW Integration Approach | 5 days | On Schedule | 2015-09-11 | 2015-09-17
Define VDW Integration Approach ( Analysis of Impact / Change on existing VDW jobs, tables and integration – Joint study VDW and TTMS (Set up meeting with VDW data architect to be structure )) | 5 days | On Schedule | 2015-09-11 | 2015-09-17
Conduct Workshop -- Mapping of TTMS Tables Attributes with VDW 8 Tables. Need to under | 3 days | Future Task | 2015-09-15 | 2015-09-17
Security Architecture - EIG | 1.75 days | Future Task | 2015-11-16 | 2015-11-18
Define Security architecture with ICE / EIG | 0.5 days | Future Task | 2015-11-16 | 2015-11-16
TLS to share the Classification of the Data. | 1 day | Future Task | 2015-11-17 | 2015-11-17
Guidelines Communication Pattern (Sync / Async) | 0.25 days | Future Task | 2015-11-18 | 2015-11-18
Security Architecture - TESS | 6 days | Future Task | 2015-09-21 | 2015-09-28
Meet with ICL to understand what is required TESS authentication | 1 day | Future Task | 2015-09-21 | 2015-09-21
Setup meeting with ICL & TESS | 1 day | Future Task | 2015-09-22 | 2015-09-22
Define Security architecture and TESS integration | 4 days | Future Task | 2015-09-23 | 2015-09-28
User Management (ICL - TMS TESS) | 8.75 days | Future Task | 2015-09-29 | 2015-10-09
TTMS-ICL Roll mapping to be finalized | 4 days | Future Task | 2015-09-29 | 2015-10-02
Define one-time initial user load and TESS role definition | 1 day | Future Task | 2015-10-05 | 2015-10-05
User transfer and termination criteria to be discussed with ICL | 1 day | Future Task | 2015-10-06 | 2015-10-06
User provisioning process to be discussed with ICL , TESS | 1 day | Future Task | 2015-10-07 | 2015-10-07
Finalize the Approval Workflow for User Authorization | 0.25 days | Future Task | 2015-10-08 | 2015-10-08
Discuss on TLS user's Account Inactive, Password Expiry, Account Lock Out with ICL | 0.25 days | Future Task | 2015-10-08 | 2015-10-08
Avoid session misuse, handle logout warning, idle session timeout | 0.25 days | Future Task | 2015-10-08 | 2015-10-08
Finalize all user provisioning requirements and get sign-off | 1 day | Future Task | 2015-10-08 | 2015-10-09
Supplementary Specifications (NFR) | 30 days | Future Task | 2015-10-01 | 2015-11-12
Analysis the Volumetric Data : For all TTMS inbound / Outbound interface | 3 days | Future Task | 2015-10-01 | 2015-10-06
Review the Volumetric Data : For all TTMS Inbound / Outbound interface | 1 day | Future Task | 2015-10-06 | 2015-10-07
Workshop - 1 Supplementary Spec | 1 day | Future Task | 2015-10-07 | 2015-10-08
User and User role management, application role | 0.5 days | Future Task | 2015-10-07 | 2015-10-07
Application scalability ,usability and performance targets | 0.5 days | Future Task | 2015-10-08 | 2015-10-08
Workshop - 2 Supplementary Spec | 7 days | Future Task | 2015-10-08 | 2015-10-19
Application Disaster recovery - SLAs | 3 days | Future Task | 2015-10-08 | 2015-10-13
Application Security | 2 days | Future Task | 2015-10-13 | 2015-10-15
Application Performance Monitoring | 2 days | Future Task | 2015-10-15 | 2015-10-19
Intermediate SAD Document Session 1 | 3 days | Future Task | 2015-10-19 | 2015-10-22
Intermediate SAD Document finalization | 3 days | Future Task | 2015-10-22 | 2015-10-27
Review Supplementary Spec (Team) | 3 days | Future Task | 2015-10-27 | 2015-10-30
Review Supplementary Spec (EA) | 3 days | Future Task | 2015-10-30 | 2015-11-04
Update Supplementary Spec | 4 days | Future Task | 2015-11-04 | 2015-11-10
Supplementary Specs SO: EA | 1 day | Future Task | 2015-11-10 | 2015-11-11
Supplementary Specs | 1 day | Future Task | 2015-11-11 | 2015-11-12
Develop/Update SAD | 17 days | Future Task | 2015-10-21 | 2015-11-13
Solution Architecture | 0 days | Future Task | 2015-11-13 | 2015-11-13
Soln. Architecture - ICL | 19 days | Future Task | 2015-10-30 | 2015-11-30
External Dependencies | 89 days? | Future Task | 2015-09-21 | 2016-01-27
Technical Design - TMS | 95 days | Future Task | 2015-09-14 | 2016-01-28
Common Components | 62 days | Future Task | 2015-09-14 | 2015-12-10
JBOSS Appframework Support for Jboss Hornet Queue Configuration – Need analysis Appframework documentation | 5 days | Future Task | 2015-09-14 | 2015-09-18
Queue Configuration and Single Queue instance with Jboss HornetQueue | 5 days | Future Task | 2015-09-21 | 2015-09-25
Setup a meeting with deepak to share the outcome of the analysis | 3 days | Future Task | 2015-09-28 | 2015-09-30
POC - JASON - JSON message schema Validator | 5 days | Future Task | 2015-10-01 | 2015-10-07
JSON File Attachment and Compression techniques | 5 days | Future Task | 2015-10-08 | 2015-10-14
Spring JMS with latest JBOSS appframework Support Analysis | 5 days | Future Task | 2015-10-15 | 2015-10-21
Spring Batch Analysis - Already have the Appframework documentation | 4 days | Future Task | 2015-10-22 | 2015-10-27
JMX control to stop and start Message listener service programmatically | 4 days | Future Task | 2015-10-28 | 2015-11-02
Design Service Layer | 2 days | Future Task | 2015-11-03 | 2015-11-04
Design Business Layer | 2 days | Future Task | 2015-11-05 | 2015-11-06
Design DAO Layer | 2 days | Future Task | 2015-11-09 | 2015-11-10
Design Security Layer - APP /EIG | 2 days | Future Task | 2015-11-11 | 2015-11-12
Design TMS Appframework Integration - RT Webservices | 1 day | Future Task | 2015-11-13 | 2015-11-13
Design Junit Approach Methodlogy | 1 day | Future Task | 2015-11-16 | 2015-11-16
Design TMS Appframework Integration - FTPS Batch | 1 day | Future Task | 2015-11-17 | 2015-11-17
Design Security Layer - APP /EIG | 1 day | Future Task | 2015-11-18 | 2015-11-18
Design Integration - EIG | 1 day | Future Task | 2015-11-19 | 2015-11-19
Design Exception and Error Handling Hierarchy | 1 day | Future Task | 2015-11-20 | 2015-11-20
Design Auditing | 1 day | Future Task | 2015-11-23 | 2015-11-23
Design Monitoring | 1 day | Future Task | 2015-11-24 | 2015-11-24
Design Configuration Management | 1 day | Future Task | 2015-11-25 | 2015-11-25
Design Service account Handling | 1 day | Future Task | 2015-11-30 | 2015-11-30
Design Build and Release Management | 1 day | Future Task | 2015-12-01 | 2015-12-01
Design Integration - VDW | 1 day | Future Task | 2015-12-02 | 2015-12-02
Publish Design: Common Components | 1 day | Future Task | 2015-12-03 | 2015-12-03
R1: Host Internal Prep Discussion With EA | 1 day | Future Task | 2015-12-04 | 2015-12-04
Update Design: Common Components | 1 day | Future Task | 2015-12-07 | 2015-12-07
R2: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2015-12-08 | 2015-12-08
SO: Sign-off ADD Updates | 1 day | Future Task | 2015-12-09 | 2015-12-09
Design: Common Components | 1 day | Future Task | 2015-12-10 | 2015-12-10
Data Model | 27 days | Future Task | 2015-09-28 | 2015-11-03
Data requirement - Analyze existing structure | 3 days | Future Task | 2015-09-28 | 2015-09-30
Review the Requirements / List of Tables & Attributes | 4 days | Future Task | 2015-10-01 | 2015-10-06
Create Logical Data Model / Domain Data Model. | 4 days | Future Task | 2015-10-07 | 2015-10-12
Create Physical Data Model. | 5 days | Future Task | 2015-10-13 | 2015-10-19
R1: Host Internal Prep Discussion With EA & Data Steward | 3 days | Future Task | 2015-10-20 | 2015-10-22
Update: Physical Data Model. | 1 day | Future Task | 2015-10-23 | 2015-10-23
R2: Review with primary stakeholders & Incorporate Comments | 5 days | Future Task | 2015-10-26 | 2015-10-30
SO: Sign-off ADD Updates | 1 day | Future Task | 2015-11-02 | 2015-11-02
DDD: Data Model | 1 day | Future Task | 2015-11-03 | 2015-11-03
TTMS Inbound | 28 days | Future Task | 2015-12-11 | 2016-01-21
SEDB | 24 days | Future Task | 2015-12-11 | 2016-01-15
Shipment Plan | 16 days | Future Task | 2015-12-11 | 2016-01-05
Processing Plan | 16 days | Future Task | 2015-12-16 | 2016-01-08
Vehicle Summary | 13 days | Future Task | 2015-12-11 | 2015-12-30
Vehicle Events | 16 days | Future Task | 2015-12-18 | 2016-01-12
Rail Shipments | 16 days | Future Task | 2015-12-23 | 2016-01-15
Rail Inspection | 16 days | Future Task | 2015-12-23 | 2016-01-15
Transit | 17 days | Future Task | 2015-12-23 | 2016-01-18
Analysis: Evaluate of RT or Based on a File. (TTMS table (Transit File) | 1 day | Future Task | 2015-12-23 | 2015-12-23
Analyze the Existing MF Job: Extracts the Data from BDM, Does Data Comparison and any Complex Enrichment. | 1 day | Future Task | 2015-12-24 | 2015-12-24
Design: Transit App Interface | 1 day | Future Task | 2015-12-28 | 2015-12-28
Design: Transit Service Interface | 1 day | Future Task | 2015-12-29 | 2015-12-29
Design: Transit DAO (Data Access Object) | 1 day | Future Task | 2015-12-30 | 2015-12-30
TTMS Design: Business Service/Web Service (Create Customized WSDL / Schema) | 1 day | Future Task | 2015-12-31 | 2015-12-31
Design EIG - Web Services (Create Customized WSDL / Schema) | 1 day | Future Task | 2016-01-04 | 2016-01-04
Create Use Case Realization. | 1 day | Future Task | 2016-01-05 | 2016-01-05
Design Business Rule validations and discard /Filter Scenarios | 1 day | Future Task | 2016-01-06 | 2016-01-06
Design Transaction Management | 1 day | Future Task | 2016-01-07 | 2016-01-07
Design Exception | 1 day | Future Task | 2016-01-08 | 2016-01-08
Design Audit and Alert /Email | 1 day | Future Task | 2016-01-11 | 2016-01-11
R1: Host Internal Prep Discussion With EA & Data Steward | 1 day | Future Task | 2016-01-12 | 2016-01-12
Update Design: Transit | 1 day | Future Task | 2016-01-13 | 2016-01-13
R2: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2016-01-14 | 2016-01-14
SO: Sign-off ADD Updates | 1 day | Future Task | 2016-01-15 | 2016-01-15
ADD: Transit | 1 day | Future Task | 2016-01-18 | 2016-01-18
Voucher - FTPR Voucher | 15 days | Future Task | 2015-12-30 | 2016-01-20
Design: Voucher Pull App Interface | 1 day | Future Task | 2015-12-30 | 2015-12-30
Design: Voucher Pull Service Interface | 1 day | Future Task | 2015-12-31 | 2015-12-31
Design: Voucher Pull DAO (Data Access Object) | 1 day | Future Task | 2016-01-04 | 2016-01-04
TTMS Design: Business Service/Web Service (Create Customized WSDL / Schema) | 1 day | Future Task | 2016-01-05 | 2016-01-05
Design EIG - Web Services (Create Customized WSDL / Schema) | 1 day | Future Task | 2016-01-06 | 2016-01-06
Create Use Case Realization. | 1 day | Future Task | 2016-01-07 | 2016-01-07
Design Business Rule validations and discard /Filter Scenarios | 1 day | Future Task | 2016-01-08 | 2016-01-08
Design Transaction Management | 1 day | Future Task | 2016-01-11 | 2016-01-11
Design Exception | 1 day | Future Task | 2016-01-12 | 2016-01-12
Design Audit and Alert /Email | 1 day | Future Task | 2016-01-13 | 2016-01-13
R1: Host Internal Prep Discussion With EA & Data Steward | 1 day | Future Task | 2016-01-14 | 2016-01-14
Update Design: Voucher | 1 day | Future Task | 2016-01-15 | 2016-01-15
R2: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2016-01-18 | 2016-01-18
SO: Sign-off ADD Updates | 1 day | Future Task | 2016-01-19 | 2016-01-19
ADD: Voucher | 1 day | Future Task | 2016-01-20 | 2016-01-20
Accrual | 15 days | Future Task | 2015-12-30 | 2016-01-20
Design: Accrual Flat App Interface | 1 day | Future Task | 2015-12-30 | 2015-12-30
Design: Accrual Service Interface | 1 day | Future Task | 2015-12-31 | 2015-12-31
Design: Accrual DAO (Data Access Object) | 1 day | Future Task | 2016-01-04 | 2016-01-04
TTMS Design: Business Service/Web Service (Create Customized WSDL / Schema) | 1 day | Future Task | 2016-01-05 | 2016-01-05
Design EIG - Web Services (Create Customized WSDL / Schema) | 1 day | Future Task | 2016-01-06 | 2016-01-06
Create Use Case Realization. | 1 day | Future Task | 2016-01-07 | 2016-01-07
Design Business Rule validations and discard /Filter Scenarios | 1 day | Future Task | 2016-01-08 | 2016-01-08
Design Transaction Management | 1 day | Future Task | 2016-01-11 | 2016-01-11
Design Exception | 1 day | Future Task | 2016-01-12 | 2016-01-12
Design Audit and Alert /Email | 1 day | Future Task | 2016-01-13 | 2016-01-13
R1: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2016-01-14 | 2016-01-14
Update Design: Accrual | 1 day | Future Task | 2016-01-15 | 2016-01-15
R2: Host Internal Prep Discussion With EA & Data Steward | 1 day | Future Task | 2016-01-18 | 2016-01-18
SO: Sign-off ADD Updates | 1 day | Future Task | 2016-01-19 | 2016-01-19
ADD: Accrual | 1 day | Future Task | 2016-01-20 | 2016-01-20
VDW - TTMS Integration Comp. | 16 days | Future Task | 2015-12-11 | 2016-01-05
Understand & Analyze Requirements | 1 day | Future Task | 2015-12-11 | 2015-12-11
Design: VDW Plan App Interface | 1 day | Future Task | 2015-12-14 | 2015-12-14
Design: VDW Service Interface | 1 day | Future Task | 2015-12-15 | 2015-12-15
Design: VDW DAO (Data Access Object) | 1 day | Future Task | 2015-12-16 | 2015-12-16
TTMS Design: Business Service/Web Service | 1 day | Future Task | 2015-12-17 | 2015-12-17
Design EIG - Web Services | 1 day | Future Task | 2015-12-18 | 2015-12-18
Create Use Case Realization. | 1 day | Future Task | 2015-12-21 | 2015-12-21
Design Business Rule validations and discard /Filter Scenarios | 1 day | Future Task | 2015-12-22 | 2015-12-22
Design Transaction Management | 1 day | Future Task | 2015-12-23 | 2015-12-23
Design Exception | 1 day | Future Task | 2015-12-24 | 2015-12-24
Design Audit and Alert /Email | 1 day | Future Task | 2015-12-28 | 2015-12-28
R1: Host Internal Prep Discussion With EA & VDW Data Steward | 1 day | Future Task | 2015-12-29 | 2015-12-29
Update Design: VDW TTMS Integration Component | 1 day | Future Task | 2015-12-30 | 2015-12-30
R2: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2015-12-31 | 2015-12-31
SO: Sign-off ADD Updates | 1 day | Future Task | 2016-01-04 | 2016-01-04
ADD: TTMS Integration Comp. for VDW. | 1 day | Future Task | 2016-01-05 | 2016-01-05
VDW - Datawarehouse Design | 7 days | Future Task | 2015-12-28 | 2016-01-06
Understand & Analyze Requirements | 1 day | Future Task | 2015-12-28 | 2015-12-28
Design: VDW Design impact analysis due to the new table creations in TTMS schema. | 1 day | Future Task | 2015-12-29 | 2015-12-29
Design: Documentation of the VDW HLD | 1 day | Future Task | 2015-12-30 | 2015-12-30
Design: Review of the VDW High Level Design document | 1 day | Future Task | 2015-12-31 | 2015-12-31
R1: Host Internal Prep Discussion With EA & Data Steward/VDW team | 1 day | Future Task | 2016-01-04 | 2016-01-04
R2: Review with primary stakeholders & Incorporate Comments (including VDW team) | 1 day | Future Task | 2016-01-05 | 2016-01-05
ADD: VDW Datawarehouse Design | 1 day | Future Task | 2016-01-06 | 2016-01-06
Vessel ETA | 15 days | Future Task | 2015-12-16 | 2016-01-07
Design: Vessel ETA App Interface | 1 day | Future Task | 2015-12-16 | 2015-12-16
Design: Vessel ETA Service Interface | 1 day | Future Task | 2015-12-17 | 2015-12-17
Design: Vessel ETA DAO (Data Access Object) | 1 day | Future Task | 2015-12-18 | 2015-12-18
TTMS Design: Business Service/Web Service (Create Customized WSDL / Schema) | 1 day | Future Task | 2015-12-21 | 2015-12-21
Design EIG - Web Services (Create Customized WSDL / Schema) | 1 day | Future Task | 2015-12-22 | 2015-12-22
Create Use Case Realization. | 1 day | Future Task | 2015-12-23 | 2015-12-23
Design Business Rule validations and discard /Filter Scenarios | 1 day | Future Task | 2015-12-24 | 2015-12-24
Design Transaction Management | 1 day | Future Task | 2015-12-28 | 2015-12-28
Design Exception | 1 day | Future Task | 2015-12-29 | 2015-12-29
Design Audit and Alert /Email | 1 day | Future Task | 2015-12-30 | 2015-12-30
R1: Host Internal Prep Discussion With EA & Data Steward | 1 day | Future Task | 2015-12-31 | 2015-12-31
Update Design: Vessel ETA | 1 day | Future Task | 2016-01-04 | 2016-01-04
R2: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2016-01-05 | 2016-01-05
SO: Sign-off ADD Updates | 1 day | Future Task | 2016-01-06 | 2016-01-06
ADD: Vessel ETA | 1 day | Future Task | 2016-01-07 | 2016-01-07
Shipping Schedule | 15 days | Future Task | 2015-12-31 | 2016-01-21
Design: Shipping Schedule App Interface | 1 day | Future Task | 2015-12-31 | 2015-12-31
Design: Shipping Schedule Service Interface | 1 day | Future Task | 2016-01-04 | 2016-01-04
Design: Shipping Schedule DAO (Data Access Object) | 1 day | Future Task | 2016-01-05 | 2016-01-05
TTMS Design: Business Service/Web Service (Create Customized WSDL / Schema) | 1 day | Future Task | 2016-01-06 | 2016-01-06
Design EIG - Web Services (Create Customized WSDL / Schema) | 1 day | Future Task | 2016-01-07 | 2016-01-07
Create Use Case Realization. | 1 day | Future Task | 2016-01-08 | 2016-01-08
Design Business Rule validations and discard /Filter Scenarios | 1 day | Future Task | 2016-01-11 | 2016-01-11
Design Transaction Management | 1 day | Future Task | 2016-01-12 | 2016-01-12
Design Exception | 1 day | Future Task | 2016-01-13 | 2016-01-13
Design Audit and Alert /Email | 1 day | Future Task | 2016-01-14 | 2016-01-14
R1: Host Internal Prep Discussion With EA & Data Steward | 1 day | Future Task | 2016-01-15 | 2016-01-15
Update Design: Shipping Schedule | 1 day | Future Task | 2016-01-18 | 2016-01-18
R2: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2016-01-19 | 2016-01-19
SO: Sign-off ADD Updates | 1 day | Future Task | 2016-01-20 | 2016-01-20
ADD: Shipping Schedule | 1 day | Future Task | 2016-01-21 | 2016-01-21
TTMS Outbound | 10 days | Future Task | 2015-11-16 | 2015-12-02
ADD: TTMS Outbound to ICL | 10 days | Future Task | 2015-11-16 | 2015-12-02
Parallel Validation - Comparator Tool | 58.5 days | Future Task | 2015-11-03 | 2016-01-28
Design: Tool App Interface | 1 day | Future Task | 2015-11-13 | 2015-11-16
Design: Tool Service Interface | 1 day | Future Task | 2015-11-06 | 2015-11-09
Design: Tool DAO (Data Access Object) | 1 day | Future Task | 2015-11-11 | 2015-11-12
TTMS Design: Business Service/Web Service (Create Customized WSDL / Schema) | 1 day | Future Task | 2015-11-12 | 2015-11-13
Create Use Case Realization. | 1 day | Future Task | 2015-11-13 | 2015-11-16
Design Business Rule validations and discard /Filter Scenarios | 1 day | Future Task | 2015-11-30 | 2015-12-01
Design Transaction Management | 1 day | Future Task | 2015-11-03 | 2015-11-04
Design Exception | 1 day | Future Task | 2015-11-06 | 2015-11-09
Design Audit and Alert /Email | 1 day | Future Task | 2015-11-13 | 2015-11-16
R1: Host Internal Prep Discussion With EA & Data Steward | 1 day | Future Task | 2015-11-17 | 2015-11-18
Update Design: Comparator Tool | 1 day | Future Task | 2015-11-20 | 2015-11-23
R2: Review with primary stakeholders & Incorporate Comments | 1 day | Future Task | 2015-11-24 | 2015-11-25
SO: Sign-off ADD Updates | 1 day | Future Task | 2015-11-30 | 2015-12-01
ADD: Comparator Tool for Parallel Validation | 1 day | Future Task | 2016-01-28 | 2016-01-28
User Management (ICL - TMS TESS) | 1 day | Future Task | 2015-11-13 | 2015-11-16
ADD: User Management (ICL - TMS TESS) | 1 day | Future Task | 2015-11-13 | 2015-11-16
Technical Design: TTMS - DDD | 1 day | Future Task | 2016-01-22 | 2016-01-22
Technical Design: TTMS - ADD | 1 day | Future Task | 2016-01-22 | 2016-01-22
Technical Design: ICE | 1 day | Future Task | 2016-01-22 | 2016-01-22
Technical Design - ICL | 1 day | Future Task | 2016-01-22 | 2016-01-22
Test Strategy and Plan | 32.5 days | Future Task | 2015-11-13 | 2016-01-04
Gather Inputs | 3 days | Future Task | 2015-11-13 | 2015-11-18
Functional Test Strategy | 9 days | Future Task | 2015-11-18 | 2015-12-03
Joint Integration Test Strategy | 9 days | Future Task | 2015-11-18 | 2015-12-03
Performance Test Strategy | 9 days | Future Task | 2015-12-01 | 2015-12-14
Cutover Strategy | 4.5 days | Future Task | 2015-12-14 | 2015-12-18
Parallel Test Strategy | 10.5 days | Future Task | 2015-12-10 | 2015-12-24
Test Plan | 5 days | Future Task | 2015-12-28 | 2016-01-04