## SolutionArchitecture Task list
Solution Architecture
Define POC
Identify POC
Workshops: Integration Architecture - ICL
Workshop: TESS Integration solution Approach for ICL
Define TMS - Inbound Wkshop # 1 (Define TMS - Inbound - Happy Path Scenario / Get Acknowledgement for each request)
Define TMS - Inbound Wkshop # 2(High Level Message Format, Error Handling)
Define TMS - Inbound Wkshop # 3 (ICL – TTMS Inbound Communication Downtime Scenarios)
Define TMS - Define TESS integration - TLS Designate Users (TESS SSO Federation- User Management & Role Management)
Define TMS - (Continue to Review the Scenarios for System Down time HLD: Error Handling, Message Sequencing.Review High Level ICE Design) | Completed
Define TMS - ICE High level Design Document – TTMS Redesign
Conduct Workshop to Communicate the Integration and Security Pattern to ICL.
Define Security architecture and TESS integration - TLS Designate Users (TESS SSO Federation)
Walkthrough of the High Level Architecture - TMS
Document the High Level Architecture - TMS
Conduct Workshop to Review the High Level Architecture for ICL.
Soln. Architecture - TMS
TTMS - Integration (TMS, ICL)
Define Architecture Goals
Document Conceptual Architecture
Identify the High-level Technical Stack along with EIG
Document To-Be Arch Context View
I1: Internal review of conceptual architecture and goals
Incorporate internal review comments
TMS Inbound Integration Approach
Define & Document TMS Inbound – (Define Integration technical Approach (Web services / FTPS))
Analyse Architecturaly Significant use case documents
W1: Conduct workshop with primary stakeholders
Analysis / Design: Message Sequencing – Integration Channels, Auditing and Monitoring.
Document: Message Sequencing – Integration Channels
Document: Auditing and Monitoring.
Finalize the Communication pattern with EA and ICE- Integration Pattern (SOAP or REST)
Finalize the Security Pattern
Document the integration approach and review internally
R1: Review the integration approach with primary stakeholders
Incorporate review comments & Republish
Communicate the Integration solution – ICL.
ICL SO: Sign-off TMS Integration Approach
TMS Outbound Real Time Integration Approach
Define TMS Outbound – (Real-Time Communication Integration Approach)
Analyse Architecturaly Significant use case documents
Analysis / Design: Message Sequencing – Integration Channels, Auditing and Monitoring.
Document: Message Sequencing – Integration Channels
Document: Auditing and Monitoring.
Finalize the Communication pattern with EA and ICE- Integration Pattern (SOAP or REST)
W1: Conduct workshop with primary stakeholders
Feasibility study for real time data communication (Identify the Source) for TTMS outbound interface (++ Analyze the N/C # 1
Workshop: Feasibility study for real time data communication (Identify the Source) for TTMS outbound interface (++ Focus the N/C. & ICE ) # 2. Document the Table Details
Technical Analyze: Error & Exception Handling - Integration Flows
Finalize the Security Pattern
Document the integration approach and review internally
R1: Review the integration approach with primary stakeholders
Communicate the solution – ICL.
Incorporate review comments & Republish
ICL SO: Sign-off TMS Integration Approach
VDW Integration Approach
Define VDW Integration Approach
Security Architecture - EIG
Define Security architecture with ICE / EIG
TLS to share the Classification of the Data.
Guidelines Communication Pattern (Sync / Async)
Security Architecture - TESS
Define Security architecture and TESS integration
User Management (ICL - TMS TESS)
TTMS-ICL Roll mapping to be finalized
Define one-time initial user load and TESS role definition
User transfer and termination criteria to be discussed with ICL
User provisioning process to be discussed with ICL , TESS
Finalize the Approval Workflow for User Authorization
Discuss on TLS user's Account Inactive, Password Expiry, Account Lock Out with ICL
Avoid session misuse, handle logout warning, idle session timeout
Finalize all user provisioning requirements and get sign-off
Supplementary Specifications
Analysis the Volumetric Data : For all TTMS inbound / Outbound interface
Review the Volumetric Data : For all TTMS Inbound / Outbound interface
Workshop - 1 Supplementary Spec
Create Supp. Spec (NFR)
Workshop - 2 Supplementary Spec
Review Supplementary Spec (EA)
Review Supplementary Spec (all)
Update Supplementary Spec
Supplementary Specs SO: EA
Supplementary Specs
Develop SAD
Collate Inputs & Publish SAD
Rest High-level Message Schema Preparation
Document architectural solution scenarios/decisions
Document logical architecture views
Document Implementation Views
Document Deployment Views
SAD Review & Sign Off
Publish SAD , Conduct Internal Review & Incorporate Review Comments
R1: Review with primary stakeholders & Incorporate Comments
SO: Sign-off Solution Architecture Document - Iteration 3
SAD
Soln. Architecture - ICL
High Level Architecture
Document ICL Integration Architecture views
Publish SAD
R1: Review with TTMS, ICE & EA stakeholders & Incorporate Comments
ICL to Incorporate Review Comments - ICL SAD
R2: Review with TTMS, ICE & EA stakeholders & Incorporate Comments
Soln. Architecture - ICL